## Product Catalog
Project Name | FOODBOX
StakeHolders/Customers/Users | SIMPLILEARN
Created By | Suman Rani
Epic | User Story ID | Feature/Title | User Story | Status | Acceptance Criteria
For an admin to manage & categorize all the food items, Keep track of user info. & should be able to see food order report filtered by date & category. (FoodBox.com_Epic_001) | US001 | Admin can change the password if he wants to. | As an Admin, I want to be able to change the password So that I can be very assured & satisfied that no one other than me can have the authority to access my E-Commerce site. | New
| US002 | Admin can manage all the food items. | As an Admin, I want to be able to manage all the food items that has been purchased by the user's and that are there available in my store So that I can have clear understanding of what food item demands the more. | New
| US003 | Admin can categorize all the food items based on food ID, availability & price. | As an Admin, I want to be able to categorize all the food items based on food ID, availability & price. So that the end user can easily get the desired food item within less time. | New
| US004 | Admin can browse the list of users who signed up & can be able to search users. | As an Admin, I want to be able to browse the list of users who signed up on my website so that I can search them later on, track and provide them better results in future. | New
| US005 | Admin can see purchase details of all the foods filtered by date & category & also create UI side of the backend. | As an Admin, I want to be able to see the purchase details filtered by date & category So that I can maintain the list of food items sold every month. | New

## Sprint Planning
Project Name | FoodBox.com
Scrum Team | Dev, QA, PO, Scrum Master etc.
Created By | Suman Rani
Epic | User Story ID | Feature/Title | User Story | Story Points | Sprint
For an admin to manage & categorize all the food items, Keep track of user info. & should be able to see food order report filtered by date & category. | US001 | Admin can change the password if he wants to. | As an Admin, I want to be able to change the password So that I can be very assured & satisfied that no one other than me can have the authority to access my E-Commerce site. | 5 | 1
| US002 | Admin can manage all the food items. | As an Admin, I want to be able to manage all the food items that has been purchased by the user's and that are there available in my store So that I can have clear understanding of what food item demands the more. | 3 | 1
| US003 | Admin can categorize all the food items based on food ID, availability & price. | As an Admin, I want to be able to categorize all the food items based on food ID, availability & price. So that the end user can easily get the desired food item within less time. | 5 | 2
| US004 | Admin can browse the list of users who signed up & can be able to search users. | As an Admin, I want to be able to browse the list of users who signed up on my website so that I can search them later on, track and provide them better results in future. | 5 | 3
| US005 | Admin can see purchase details of all the food items filtered by date & category. | As an Admin, I want to be able to see the purchase details filtered by date & category So that I can maintain the list of food items sold every month. | 8 | 3

## Sheet1
TestCaseID | UserStoryID | Feature | User Story
TC_DL_001 | US001 | Admin can manage all the food items and users can search for the food items based on the categories like food name, availability & price set by admin. | As a first-time user to the application, I want to be able to categorize all the food items based on availability, food ID & price So that the consumer can easily search for the desired food.
TC_DL_002 | US002 | Admin can track all the product related details using URI or endpoint using postman tool. | As an owner of the application and admistrator of website, I want to be able to see the purchse report of all the food items sold filtered by date & category with the help of endpoint or URI So that I can list out the food that are in high quality.

## Tasks
QA Tasks | Developer Tasks
Reviewing User Stories | Reviewing User Stories
Creating Test Cases | Setting up Development Environment
Setting up Test Environment | Developing Programs
Creating Test Data | Code Review
Executing Manual Tests | Creating Unit Test Cases
Automation Setup | Executing Unt Tests
Automation Design | Merging Code
Automating Test Cases | Creating Builds
Re-Testing Bugs | Fixing Bugs